## Issues
ID | Severity | Status | Area | Problem | Solution / Fix | Location | Done?
O-1 | P1 | Open | Frontend | reCAPTCHA still falls back to Google test key and sends 'dev_bypass_token' when grecaptcha is absent -> bot protection bypassable. | Remove test-key fallback and dev_bypass_token; read site key from environment; block submit without a real token. | contact.component.ts:82,133,146
O-2 | P1 | Open | Backend | 40+ controller catches return $e->getMessage() with HTTP 500 (info disclosure; 404/422 flattened). | Log $e internally; return a generic message; let 404/422 propagate. | LeadController.php:41,206 / SettingController.php:35 / LandingPageController.php:139,150,171
O-3 | P1 | Open | Backend | No forgot/reset-password flow exists. | Add a secure forgot/reset-password route + mail. | routes/api.php
O-4 | P2 | Open | Frontend | JWT + user stored in localStorage (XSS-exfiltratable). | Move token to an httpOnly secure cookie. | auth.service.ts:19-49
O-5 | P2 | Open | Frontend | alert() used for user-facing errors in ~12 places. | Introduce a shared toast/notification service. | settings/leads/projects/pages/contact:141
O-6 | P2 | Open | Backend | Setting model has no $casts (bool/json values uncast). | Add $casts to the Setting model. | Setting.php
N-1 | P1 | New | Backend | updateBulk passes raw $request->all() into updateOrCreate over ANY key -> a user with edit-settings can write sensitive keys (recaptcha_secret_key, mail_password, SMTP). | Validate against an allow-list of known setting keys via a FormRequest before bulk upsert. | SettingController.php:71 + SettingService.php:38-46
N-2 | P1 | New | Backend | Dynamic landing form: empty schema -> validate([]) checks nothing; standard fields taken from raw input with no validation/consent; $field['name']/['type'] accessed without isset -> 500 on malformed schema. | Require a non-empty schema; guard with isset; enforce max lengths; require privacy_consent like the JSON lead path. | LandingPageController.php:90-128
N-3 | P2 | New | Backend | Public submitForm catch returns $e->getMessage() with 500 to anonymous users. | Return a generic message; log the exception. | LandingPageController.php:136
N-4 | P2 | New | Backend | Leads export gated only by an in-controller abort_unless; the route has no permission middleware (no defense-in-depth). | Add ->middleware('permission:export-leads') on the export route. | routes/api.php:82
N-5 | P2 | New | Backend | Dashboard lead counts are global; an agent with only view-unassigned-leads sees total lead volume. | Scope dashboard counts to the same ownership filter as the lead list. | DashboardController.php
N-6 | P2 | New | Frontend | Conversion event ships a placeholder id: gtag(... send_to:'AW-XX/lead'). | Source the conversion id from settings/env, or remove until configured. | contact.component.ts:172
N-7 | P3 | New | Frontend | Count-up animation uses setInterval with no ngOnDestroy cleanup (minor leak). | Implement OnDestroy to clear the interval/timers. | home.component.ts:281
N-8 | P3 | New | Frontend | settings save writes document.documentElement without isPlatformBrowser guard. | Wrap the DOM write in isPlatformBrowser for consistency. | settings.component.ts:278
F-1 | P0 | Done | Frontend | Stored XSS via raw GTM HTML injection. | Fixed: validated container id + real <script> element. | seo.service.ts:58-101
F-2 | P0 | Done | Frontend | Stored XSS via bypassSecurityTrustHtml on API content. | Fixed: removed; plain [innerHTML] (sanitized). | landing-page.component.ts:156
F-3 | P0 | Done | Backend | Public lead mass-assignment. | Fixed: blocklist in LeadDTO + whitelist in UseCase. | LeadDTO.php:18
F-4 | P0 | Done | Backend | reCAPTCHA bypass (backend). | Fixed: fail-closed in prod; submitForm verifies token. | RecaptchaService.php:24-49
F-5 | P0 | Done | Repo | Committed dangerous debug scripts. | Fixed: all removed. | repo root
F-6 | P1 | Done | Backend | CORS allowed_origins = ['*']. | Fixed: explicit env-driven origins. | config/cors.php
F-7 | P1 | Done | Backend | Project N+1 ($appends accessor). | Fixed: removed; uses relation. | Project.php
F-8 | P1 | Done | Backend | Missing DB indexes. | Fixed: indexes added. | 2026_06_28_095235 migration
F-9 | P1 | Done | Backend | Backups not configured. | Fixed: config/backup.php published + scheduled. | config/backup.php
F-10 | P1 | Done | Backend | privacy_consent not validated/stored. | Fixed: validated, cast, stored with timestamp. | StoreLeadRequest + migration
F-11 | P1 | Done | Frontend | No production env (dev host shipped). | Fixed: environment.prod.ts + fileReplacements. | environment.prod.ts / angular.json
F-12 | P1 | Done | Frontend | SSR-unsafe layout (document/getBrowserLang). | Fixed: guarded with isPlatformBrowser. | public-layout.component.ts
F-13 | P1 | Done | Frontend | Duplicate auth interceptors. | Fixed: consolidated to one. | app.config.ts
F-14 | P1 | Done | Frontend | Hardcoded canonical + fictitious /ar hreflang. | Fixed: origin-derived; bogus alternate removed. | app.component.ts
F-15 | P2 | Done | Backend | composer minimum-stability: dev. | Fixed: set to stable. | composer.json:78
F-16 | P2 | Done | Backend | Project hard-delete / missing casts / queued email / TestController. | Fixed: SoftDeletes+casts, ShouldQueue, TestController removed. | Project.php / NewLeadNotification

## Summary
Real Estate Website — Issue Tracker
Code quality: ~9/10 ¦ Production readiness: ~7.5/10
| P0 | P1 | P2 | P3 | Total
Open | 0 | 3 | 3 | 0 | 6
New (from features) | 0 | 2 | 4 | 2 | 8
Fixed | 5 | 9 | 2 | 0 | 16
Priority: fix the 3 P1 items first (O-1 reCAPTCHA FE, N-1 settings allow-list, N-2 landing form), then O-2 exception leakage.